## WBS
Work Breakdown Structure | [5 empty] | Pirelli Research Group.S.R.L
© 2017 by Vertex42.com
| Project Start | 23/01/2023 |  |  |  |  | Work Breakdown Structure
35 | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Research |  |  |  |  | ◄ A Conditional Formatting rule formats Level 1 tasks
2 | 1.1 | Analysing and studying of the assignment | Imran, Oliverio, Pavoni, Rajapaksha | 2023-01-23 | 2023-01-26
2 | 1.2 | Research and data collection | Imran, Oliverio, Pavoni, Rajapaksha | 2023-01-23 | 2023-01-26
3 | 1.2.1 | WBS, RACI, OBI compilation | Imran, Rajapaksha | 2023-01-23 | 2023-01-24
1 | 2 | Development
2 | 2.1 | Choice of language to use (python) | Imran, Rajapaksha | 2023-01-27 | 2023-01-28 | * Decide with group *
2 | 2.2 | Choice of libraries to use | Pavoni | 2023-01-27 | 2023-01-28
3 | 2.2.1 | Creating a basic script / source code development | Pavoni | 2023-01-27 | 2023-01-28
3 | 2.2.2 | Testing the script | Pavoni | 2023-01-27 | 2023-01-28
4 | 2.01.03 | Solving bugs | Imran, Oliverio, Pavoni, Rajapaksha | 2023-01-27 | 2023-01-28 | * Group help *
2 | 2.2 | Advance search on google to resolve unspected problems | Imran, Oliverio, Pavoni, Rajapaksha | 2023-01-27 | 2023-01-28 | * Group help *
1 | 3 | Submit process
2 | 3.1 | Creating and compiling the markdown file | Oliverio | 2023-01-29 | 2023-01-29
◄ Add new rows ABOVE this one.